## Sheet1
Facility Name | Project Title | Current Phase | Occupancy Complete | Project Manager
Angell Street 164 | Cafe conversion to bookstore | Design | 2022-01-31 | Shirley Ng
Annmary Brown Memorial Library | Exterior renewal and crypt dehumidification | Design | 2022-08-19 | Jessica Galatro
Barus + Holley | Lobby fire code upgrades | Design | 2022-01-28 | Shirley Ng
Barus + Holley | Install public art (Hirst's "Earth Air Fire and Water") | Design | 2022-01-31 | Shirley Ng
BioMed GG | Green metal roof upgrade | Construction | 2022-06-30 | Paul Griffin
BioMed CARE Suite | CARE suite renovations (rms 341, 343, 347) | Construction | 2021-09-24 | Jessica Galatro
BioMed Center | Emergency distribution | Design | 2022-09-01 | Yi Vizard
Bowen Street 181 | Brown to Brown - 181 Bowen Street house construction | Design | 2022-03-11 | Raymond Bourcier
Brook Street 248-254 | Brook Street Residence Halls | Design | 2023-08-17 | Richard Jackson
Brown/RISD Catholic Center | Brown/RISD Catholic Center | Construction | 2021-10-29 | Paul Griffin
Campus | Public art renewal allowance | Request | 2021-10-31 | Shirley Ng
Campus | Area Coordinator apartments renovations and office space (Residential Life hires) | Construction | 2021-11-30 | Yi Vizard
Campus | STUDY : Center for Artistic Design & Production (BAI) new shop facility | Planning | 2022-01-31 | Paul Griffin
Campus | Exterior paint allowance | Construction | 2022-06-30 | Gary Martins
Campus | Minor masonry allowance | Construction | 2022-06-30 | Gary Martins
Campus | Parking lot allowance | Construction | 2022-06-30 | Gary Martins
Campus | Pathway allowance | Construction | 2022-06-30 | Gary Martins
Campus | ADA allowance | Design | 2022-06-30 | Shirley Ng
Campus | Fit-out for academic new hire offices | Construction | 2022-08-16 | Yi Vizard
Campus | Energy conservation and GHG reduction projects | Request | 2023-03-01 | Yi Vizard
Campus /Multiple | Decarbonization Roadmap: Install HTHW meters for thermal load verification | Construction | 2021-11-30 | Andrew Mayes
Campus /Multiple | Multi-building interior paint refresh | Construction | 2021-12-30 | Gary Martins
Campus /Multiple | Meeting room hybrid AV | Design | 2021-12-31 | Joanna Saltonstall
Campus /Multiple | Strobic fan replacement allowance | Construction | 2021-12-31 | Paul Griffin
Campus /Multiple | Fire escape inspection and repair | Construction | 2021-12-31 | Paul Griffin
Campus /Multiple | Replace domestic hot water heaters | Construction | 2021-12-31 | Paul Griffin
Campus /Multiple | Lab Ventilation Management Program upgrades | Design | 2022-04-01 | Andrew Mayes
Campus /Multiple | Minor roof repair allowance | Construction | 2022-06-30 | Gary Martins
Campus /Multiple | Classroom finish allowance | Construction | 2022-06-30 | Gary Martins
Campus /Multiple | Leak remediation in BMC, Marston Boathouse, Charlesfield Street 38 | Request | 2022-06-30 | Shirley Ng
Campus /Multiple | Miscellaneous minor work (Provost) | Design | 2022-06-30 | Yi Vizard
Campus /Multiple | Controller replacement allowance | Construction | 2022-08-31 | Paul Griffin
Campus /Multiple | Decarbonization Roadmap: Heat exchanger replacementsin preparation for lowering of CHP supply temperature | Construction | 2022-11-15 | Andrew Mayes
Campus /Multiple | Strobic fan replacement allowance | Design | 2022-12-30 | Paul Griffin
Campus /Multiple | Energy efficiency charge recovery | Request | 2024-06-30 | Yi Vizard
Campus/Multiple | Fumehood allowance | Construction | 2022-01-31 | Andrew Mayes
Churchill House | Churchill renovation and addition | Design | 2023-08-01 | Joanna Saltonstall
Faunce House | Stuart Theatre interior renewal | Design | 2022-01-21 | Raymond Bourcier
Geo-Chem Building | Water intrusion investigation | Construction | 2021-09-30 | Paul Griffin
Geo-Chem Building | Fumehood allowance | Planning | 2021-12-31 | Andrew Mayes
Granoff Center for Creative Arts | Solar blind repair | Design | 2021-11-05 | Raymond Bourcier
John Carter Brown Library | Replace existing air handler units | Construction | 2021-11-30 | Paul Griffin
John Hay Library | Elevator & lift allowance | Construction | 2021-11-30 | Raymond Bourcier
Lincoln Field Building | Building renovation | Construction | 2022-08-22 | Joanna Saltonstall
List Art Building | Update HVAC system at Bell Gallery | Design | 2022-07-31 | Jessica Galatro
MacMillan Hall | DEEPS new hires Trace Metals Lab (Ibarra, Budde) | Construction | 2022-04-01 | Jessica Galatro
Manning Hall | Interior finish renewal at chapel | Design | 2022-12-30 | Joanna Saltonstall
Meehan Auditorium | Meehan Team Experience Phase 1 | Construction | 2021-09-17 | Paul Griffin
Meehan Auditorium | Core renewal exterior and HVAC upgrades | Construction | 2021-11-05 | Paul Griffin
Nelson Fitness Center and Katherine Moran Coleman Aquatics Center | Domestic hot water tank replacement | Construction | 2021-10-31 | Raymond Bourcier
Olney Margolies Athletic Center | Upgrade electrical service | Construction | 2021-10-29 | Joanna Saltonstall
Page-Robinson Hall | Selective interior finishes | Design | 2022-12-30 | Joanna Saltonstall
Performing Arts Center | Performing Arts Center | Construction | 2022-11-14 | Matt Cate
Pizzitola Sports Center | Replace kalwall | Design | 2022-09-01 | Yi Vizard
Rhode Island Hall | Repair tunnel leaks | Construction | 2022-04-01 | Gary Martins
Rockefeller Library | Racial Justice study center (Rms 224,266,227) | Planning | 2022-01-01 | Yi Vizard
Sayles Hall | Update air handling unit controls | Design | 2022-06-30 | Jessica Galatro
Sharpe Refectory | Roof repairs | Construction | 2021-12-31 | Paul Griffin
Sharpe Refectory | Repaint stained ceiling areas | Construction | 2022-01-15 | Gary Martins
Ship Street 070 | Boiler replacement | Design | 2021-11-30 | Raymond Bourcier
Ship Street 070 | Cooling tower and HVAC upgrades | Design | 2021-12-31 | Jessica Galatro
Slater Hall | Replace remaining emergency district generator | Design | 2022-09-30 | Andrew Mayes
University Hall | Mitigate water intrusions | Construction | 2021-11-01 | Gary Martins
Utilities/Infrastructure | Utility systems renewal and upgrade Phase 6 | Design | 2022-06-30 | Andrew Mayes
Vartan Gregorian Quad | Chiller replacement | Construction | 2021-10-15 | Paul Griffin
Watson Center for Information Technology | Hybrid teaching classroom AV for CS | Construction | 2022-01-14 | Jessica Galatro
Watson Center for Information Technology | Breaker and key interlocks replacement | Design | 2022-04-01 | Andrew Mayes