## Sheet1
Facility Name | Project Title | Current Phase | Occupancy Complete | Project Manager
Alumnae Hall | Updates to Gate Space for Campus Life | Construction | 2024-06-03 | Gary Martins
Alumnae Hall | OMAS Office Needs | Construction | 2024-06-17 | Gary Martins
Andrews Hall | Elevator Replacement | Design | 2024-09-02 | Raymond Bourcier
Andrews Hall | GRU Replacement (B44) | Design | 2024-08-30 | Thomas Foskett
Andrews Hall | Replace Carpet Tiles with VCT Flooring | Design | 2024-08-29 | Yi Vizard
Andrews House | Cogut Institute Renovations | Construction | 2024-08-30 | Shirley Ng
Barus & Holley | Phase 3 Renewal | Construction | 2025-08-29 | Jarred Jackson
Barus & Holley | Student Space Renovation (010) | Construction | 2024-08-15 | Yi Vizard
Barus & Holley | Annual Structural Allowance | Design | 2024-07-15 | Yi Vizard
Bio-Medical Center | Flume Room Improvements | Design | 2024-04-30 | Jarred Jackson
Bio-Medical: CARE | CARE Consolidation & Barrier Expansion | Design | 2024-08-30 | Jarred Jackson
Brown Stadium | Stadium Track Resurfacing | Construction | 2024-06-28 | Raymond Bourcier
Brown Street 070 | Chilled Water Systems Upgrade | Construction | 2024-09-01 | Yi Vizard
Campus | Exterior Painting Allowance | Construction | 2024-06-30 | Gary Martins
Campus | Minor Masonry Allowance | Construction | 2024-06-30 | Gary Martins
Campus | Minor Roofing Allowance | Construction | 2024-06-30 | Gary Martins
Campus | Pathway Allowance | Construction | 2024-06-30 | Gary Martins
Campus | Sidewalks Allowance | Construction | 2024-06-30 | Gary Martins
Campus | Parking Lots Allowance | Construction | 2024-06-30 | Gary Martins
Campus | Misc. Minor Allowance | Design | 2024-08-15 | Gary Martins
Campus | BMS Controllers Allowance | Construction | 2025-06-30 | Robert McCabe
Campus | HVAC Controls | Construction | 2025-06-30 | Robert McCabe
Campus | Utility Systems Renewal and Upgrades (Ph 7 - Project 6) | Construction | 2025-09-26 | Robert McCabe
Campus | Decarbonization Roadmap | Construction | 2039-12-31 | Robert McCabe
Campus | Utility Systems Renewal and Upgrades (Ph 7 - Project 4 Elec MP) | Design | 2024-06-30 | Robert McCabe
Campus | OIT Specialty Services Relocation | Design | 2024-09-30 | Steven Ferrara
Campus | Fall Protection Allowance | Construction | 2024-06-30 | Thomas Foskett
Campus | Event Space Allowance | Construction | 2024-06-30 | Yi Vizard
Campus | New Hire Offices & Expansion Space Summer 2023 | Construction | 2024-07-01 | Yi Vizard
Corliss-Brackett | ADA Lift Replacement | Construction | 2024-04-30 | Thomas Foskett
Davol Square 001 | Haffenreffer Collections Research Center | Design | 2025-09-01 | Steven Ferrara
Faculty Club | New Ovens | Design | 2024-06-19 | Thomas Foskett
Field, Meister-Kavan (Turf) | Indoor Turf Facility | Design | 2026-01-06 | Steven Ferrara
Geo-Chem Building | Geo-Chem PCHW & CA Renewal | Design | 2024-06-28 | Jarred Jackson
Hemisphere Building | CareerLAB Office Growth and Refresh | Design | 2024-07-01 | Yi Vizard
Jewelry District | PILOT Street Abandonment (Elm & Richmond Streets) | Design | 2024-07-31 | Jessica Galatro
John Hay Library | Exterior Restoration and Repairs | Design | 2025-06-30 | Thomas Foskett
Lloyd Avenue 295 | Athletics Staff Growth | Design | 2024-07-31 | Steven Ferrara
Multiple | Multiple Building Water Intrusion Preliminary Assessment | Design | 2025-06-27 | Steven Ferrara
Multiple | Fire Alarm Panels | Construction | 2025-06-30 | Thomas Foskett
Multiple | Core Renewal ADA Gap Projects | Construction | 2025-08-30 | Yi Vizard
New Pembroke | Res Hall Renewal | Construction | 2024-08-16 | Paul Griffin
Page-Robinson Hall | Interior Renewal | Design | 2024-08-31 | Shirley Ng
Richmond Street 233 | New Building ¦ Integrated Life Sciences Building (ILSB) | Design | 2027-01-29 | Jessica Galatro
Richmond Street 300 | 300 Richmond 2nd floor Renovation | Construction | 2024-05-17 | Jessica Galatro
Rockefeller Library | Interior Shell Renewal | Construction | 2025-04-30 | Yi Vizard
Salomon Center For Teaching | Lobby Cosmetic Upgrades | Design | 2024-08-08 | Paul Griffin
Sharpe Refectory | Small Elevator Loading Dock Jack Replacement | Construction | 2024-05-30 | Raymond Bourcier
Ship Street 070 | NMR Compressor Installation | Construction | 2024-05-31 | Jessica Galatro
Sidney E. Frank Hall For Life Sciences | 4th Floor Carney Institute Renovations | Design | 2024-08-15 | Jarred Jackson
South Main Street 121 | Bus Duct | Construction | 2024-08-30 | Raymond Bourcier
South Main Street 121 | Replace Air Handling Units | Design | 2024-04-26 | Raymond Bourcier
South Main Street 121 | Fire Alarm/Protection/Egress Investigation | Design | 2024-06-30 | Raymond Bourcier
South Main Street 121 | Roof Replacement and Facade Repairs | Design | 2024-08-30 | Raymond Bourcier
South Street Landing | Transition to Hybrid Use | Design | 2024-07-31 | Joanna Saltonstall
Stimson Avenue 002 | Fire Compliant Door Release | Design | 2024-09-06 | Shirley Ng
Utilities/Infrastructure | Utility Systems Renewal & Upgrades (Ph 7 - Project 1 & 2) | Construction | 2024-09-16 | Robert McCabe
Verney-Woolley Hall: Pembroke Quad | CHW Connection | Design | 2025-06-27 | Thomas Foskett
Watson Center For Information Technology | OIT Data Center Phase 1 | Construction | 2024-05-06 | Robert McCabe
Watson Center For Information Technology | Replace CRAC Units & Controls | Design | 2024-12-19 | Robert McCabe