## Sheet1
Facility Name | Project Title | Current Phase | Occupancy Complete | Project Manager
Angell Street 164 | Cafe Conversion to Bookstore | Design | 2022-02-15 | Shirley Ng
Annmary Brown Memorial Library | Exterior Renewal and Crypt Dehumidification | Design | 2022-08-19 | Jessica Galatro
Barus & Holley | Engineering: Computational New Hire - Mauro Rodriguez - BH Rm 455 | Construction | 2022-01-31 | Yi Vizard
Barus & Holley | Install Public Art (Hirst's "Earth Air Fire and Water") | Construction | 2022-02-15 | Shirley Ng
Barus & Holley | Lobby Fire Code Upgrades | Construction | 2022-02-15 | Shirley Ng
Bio-Medical Center | Emergency Distribution | Construction | 2022-09-01 | Yi Vizard
BioMedical: GG | Green Metal Roof Upgrade | Construction | 2022-06-30 | Paul Griffin
Bowen Street 181 | Construction (Brown to Brown) | Construction | 2022-05-23 | Raymond Bourcier
Brook Street 248-254 | Brook Street Residence Halls | Design | 2023-08-17 | Richard Jackson
Brown Stadium | Stadium Track Resurfacing | Planning | 2022-08-01 | Andrew Mayes
Campus | Parking Lot Allowance | Construction | 2022-06-30 | Gary Martins
Campus | Decarbonization Roadmap | Construction | 2022-11-16 | Andrew Mayes
Campus | STUDY - Center for Artistic Design & Production (BAI) New Shop Facility | Planning | 2022-05-31 | Paul Griffin
Campus | ADA Allowance | Planning | 2022-06-30 | Shirley Ng
Campus | Energy Conservation and GHG Reduction Projects FY22-FY23 | Planning | 2023-03-01 | Yi Vizard
Churchill House | Churchill Renovation and Addition | Design | 2023-08-01 | Joanna Saltonstall
Engineering Research Center | New Hire Lab fit up (Nora Ayanian) rm 345 - Coordinated drones | Design | 2022-08-15 | Jessica Galatro
Engineering Research Center | New Hire lab fit up (Monica Martinez), rm 345, Fluids | Design | 2023-08-27 | Jessica Galatro
Faunce House | Stuart Theatre Interior Renewal | Construction | 2022-01-21 | Raymond Bourcier
Geo-Chem Building | STUDY Chemistry New Hire - Organic Chemist (McDonald) | Design | 2022-08-28 | Jessica Galatro
Geo-Chem Building | Fumehood Allowance | Planning | 2022-12-31 | Andrew Mayes
John Carter Brown Library | Accessible West Entry | Design | 2022-11-30 | Richard Jackson
Lincoln Field Building | Renovation | Construction | 2022-08-22 | Joanna Saltonstall
List Art Building | Update HVAC System at Bell Gallery | Design | 2022-07-31 | Jessica Galatro
MacMillan Hall | DEEPS New Hires Trace Metals Lab (Ibarra, Budde) | Construction | 2022-06-30 | Jessica Galatro
MacMillan Hall | Life Safety Upgrades | Design | 2022-08-26 | Jessica Galatro
Meehan Auditorium | Core Renewal Exterior and HVAC Upgrades | Construction | 2022-01-14 | Paul Griffin
Meiklejohn House | Conference room paint, furniture & AV Equipment | Construction | 2022-04-28 | Gary Martins
Multiple | Decarbonization - Metering | Construction | 2022-01-28 | Andrew Mayes
Multiple | Fumehood Allowance | Construction | 2022-01-31 | Andrew Mayes
Multiple | Multi-building Interior Paint Refresh | Construction | 2022-06-30 | Gary Martins
Multiple | Classroom Finish Allowance | Construction | 2022-06-30 | Gary Martins
Multiple | Brown Dining Services Appliance Upgrades | Construction | 2022-06-30 | Gary Martins
Multiple | Miscellaneous Minor Work (Provost) | Construction | 2022-06-30 | Yi Vizard
Multiple | Controller Replacement Allowance | Construction | 2022-08-31 | Paul Griffin
Multiple | Fall Protection Allowance FY21 and FY22 | Construction | 2024-06-30 | Andrew Mayes
Multiple | Lab Ventilation Management Program Upgrades | Design | 2022-04-01 | Andrew Mayes
Multiple | Leak Remediation in BMC, Marston Boathouse, 38 Charlesfield | Design | 2022-06-30 | Shirley Ng
Multiple | Strobic Fan Replacement Allowance | Design | 2022-12-30 | Paul Griffin
Multiple | Exterior Paint: 84 Benevolent Street and 125 -127 Waterman Street. | Request | 2022-06-30 | Gary Martins
Olney Margolies Athletic Center | Upgrade Electrical Service | Construction | 2022-01-31 | Joanna Saltonstall
Page-Robinson Hall | Selective Interior Finishes | Design | 2022-11-30 | Joanna Saltonstall
Partridge Hall & Annex | Renovations to Partridge House - Phase 1 | Design | 2022-09-01 | Yi Vizard
Peforming Arts Center | Performing Arts Center | Construction | 2022-11-14 | Matt Cate
Pizzitola Sports Center | Replace Kalwall | Design | 2022-09-01 | Yi Vizard
Power Street 126 | Brown to Brown - 126 Power Street Renovation | Design | 2022-10-31 | Raymond Bourcier
Rhode Island Hall | Repair Tunnel Leaks | Construction | 2022-04-01 | Gary Martins
Rockefeller Library | Water Intrusion Remediation | Design | 2022-03-01 | Gary Martins
Rockefeller Library | Racial Justice Study Center (Rms 224,266,227) | Design | 2022-07-01 | Yi Vizard
Rockefeller Library | Cosmetic Upgrades and Wayfinding Signage Upgrades | Design | 2022-08-31 | Yi Vizard
Sayles Hall | Interior Renewal | Construction | 2022-06-30 | Joanna Saltonstall
Sayles Hall | Update Air Handling Unit Controls | Design | 2022-08-19 | Jessica Galatro
Sharpe Refectory | Roof Repairs | Construction | 2022-01-31 | Paul Griffin
Sharpe Refectory | Repaint Stained Ceiling Areas | Construction | 2022-02-05 | Gary Martins
Ship Street 070 | Boiler Replacement Allowance | Construction | 2022-01-31 | Raymond Bourcier
Ship Street 070 | High Priority Envelope Repairs | Construction | 2022-08-31 | Yi Vizard
Ship Street 070 | Faculty Retention - Reconfigure Rm 339 | Design | 2022-08-15 | Jessica Galatro
Ship Street 070 | Cooling Tower and HVAC Upgrades | Design | 2022-12-31 | Jessica Galatro
Slater Hall | Replace Remaining Emergency District Generator | Design | 2022-09-30 | Andrew Mayes
Stevenson Field | CLS Video Scoreboard Installation | Construction | 2022-02-01 | Joanna Saltonstall
University Hall | Campus Moves Cosmetic Upgrades | Construction | 2022-01-31 | Yi Vizard
Utilities/Infrastructure | Utility Systems Renewal and Upgrade Phase 6 | Design | 2022-06-30 | Andrew Mayes
Watson Center for Information Technology | Hybrid Teaching Classroom AV for CS | Construction | 2022-02-15 | Jessica Galatro
Watson Center for Information Technology | Breaker and Key Interlocks Replacement | Construction | 2022-06-30 | Andrew Mayes
Watson Center for Information Technology | OIT Data Center Phase 1 | Design | 2022-09-30 | Andrew Mayes
Watson Center for Information Technology | Replace CRAC Units and Replace Controls | Planning | 2022-12-30 | Andrew Mayes